MSc Project Progress Summary

Student: Faisal Aleem   |   Supervisor: Janusz   |   IS4T702 MSc Computer Science with AI

Next Meeting: Monday 3 August 2026, 10:00am, Microsoft Teams

Completed Deliverables

| Item | Description | Status |
| --- | --- | --- |
| Ethics Form | USW Faculty Research Ethics form completed, signed by Faisal Aleem (09 June 2026). All 32 applicable checkboxes completed. Awaiting supervisor signature. | Complete |
| Literature Review | Chapter 2 complete: ~3,500 words across 12 sections. 50 real Harvard-cited references. Includes dataset tables, preprocessing pipeline diagram, 4 algorithm pseudocode boxes, fairness metrics table, technique comparison table, Gantt chart, and 4 embedded matplotlib visualisations. | Complete |
| Methodology | Chapter 3 complete: ~2,500 words across 13 sections. Covers research philosophy (positivism), deductive approach, experimental design specification, dataset justification, 5 experimental conditions, classifier and technique selection, fairness metric selection, reproducibility, validity, and ethics. | Complete |
| Gantt Chart | 14-week project Gantt chart created in both visual (chat) and Excel formats covering 7 phases, 21 tasks, and 8 milestones from June 9 to September 11, 2026. | Complete |
| Prototype Code | prototype.py: working Python script implementing the full experimental pipeline using AIF360. Covers all 5 experimental conditions, 4 fairness metrics, CSV output, and bar chart generation. requirements.txt and README.md included. | Complete |
| Preliminary Results | Results generated for both datasets across all 5 conditions. Comparison bar charts and accuracy-fairness trade-off plots produced and documented in this report. | Complete |

Table P1: Status of All Project Deliverables

Current Progress vs Project Timeline

The project is on schedule. Weeks 1 and 2 deliverables (ethics form and literature review) are complete. The prototype and preliminary results represent ahead-of-schedule progress on weeks 4 to 7 (prototype development) and weeks 7 to 9 (experimentation). The methodology chapter was also completed ahead of the planned week 8 dissertation writing phase.

Next Steps (Weeks 3 to 7: July 2026)

- Finalise experimental design: confirm hyperparameter choices for all techniques and document in Chapter 4 (Implementation).

- Extend prototype to COMPAS dataset with race as protected attribute.

- Add random forest and gradient boosting classifiers to enable multi-classifier comparison.

- Run full experimental suite with multiple random seeds (5 seeds) to assess result stability.

- Apply SHAP and LIME explainability analysis to examine feature attribution changes under each technique.

- Begin Chapter 4 (Implementation) and Chapter 5 (Results and Analysis).

Files Included in This Submission

- Chapter2_Literature_Review_Revised.docx — Full Chapter 2 with visualisations

- Chapter3_Methodology.docx — Full Chapter 3

- Preliminary_Results_Report.docx — This document

- prototype.py — Main experimental Python script

- requirements.txt — Python dependencies

- results_adult.csv — UCI Adult results data

- results_compas.csv — COMPAS results data

- README.md — Project and code documentation